GMOS-48: Risk Identification and Management approach

Risks for the project were identified through team discussions, a review of system requirements, and consideration of key technical components, including Next.js, Supabase, and Stripe integration. Each risk was then assessed based on its likelihood of occurrence and the potential impact on the overall project.

A structured method has been used to document each risk, including a clear description, its likelihood and impact (rated as low, medium, or high), an appropriate mitigation strategy, and a designated team member responsible for monitoring and managing it.

This approach ensures that risks are not only recognised early but are also continuously monitored and addressed throughout the project lifecycle.

| Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Inaccurate handling of variable-weight products (e.g., turkey, lamb) leads to incorrect estimated pricing.. | High | High | Clearly define weight ranges and display estimated pricing with disclaimers; confirm final price in-store | Backend Dev |
| R2 | Overselling products due to poor inventory synchronisation during high-demand periods (Christmas orders) | High | High | Implement real-time inventory updates in Supabase and restrict ordering when stock limits are reached. | Backend Dev |
| R3 | Stripe payment integration failure or incorrect deposit handling | Medium | High | Use Stripe test mode, validate payment flow, and implement error handling for failed transactions. | Backend Dev |
| R4 | Failure to store or retrieve data correctly from Supabase due to incorrect queries or schema design | Medium | High | Validate database schema, test queries thoroughly, and perform integration testing | Backend Dev |
| R5 | Poor user experience due to unclear checkout flow or complex UI design. | Medium | Medium | Conduct UI testing with wireframes and mockups; simplify checkout steps | UI Designer |
| R6 | Client requirements ambiguity regarding the deposit amount and pricing rules. | High | High | Confirm requirements with the client and document all assumptions clearly in scope and design | Scrum Master |
| R7 | Data inconsistency between frontend and backend (e.g., cart vs database mismatch) | Medium | High | Implement validation checks and consistent API responses | Backend Dev |
| R8 | Security risks related to storing customer data (email, phone, order details). | Low | High | Use Supabase authentication and secure API practices; avoid exposing sensitive data | Backend Dev |
| R9 | Team members unfamiliar with Next.js, Supabase, or Stripe are causing delays | Medium | Medium | Conduct learning sessions and share documentation among team members | Scrum Master |
| R10 | API design inconsistencies leading to integration issues between the frontend and backend. | Medium | Medium | Define API endpoints clearly and document request/response formats. | Backend Dev |
| R11 | Failure in the email notification system (order confirmation, reminders) | Low | Medium | Test email service integration and implement a fallback/retry mechanism | Backend Dev |
| R12 | System performance issues under peak load (e.g., many users placing orders at once) | Low | High | Use efficient queries and optimise frontend rendering; rely on scalable cloud services | Backend Dev |